## LAMPIRAN G-1
LAMPIRAN G-1
OPERATIONAL AVAILABILITY SURVEILLANCE
Aircraft Type: |  |  |  | DAUPHINE AS365N3
Date: |  |  |  | 2024-04-08
Tail No |  | Time of the day | [47 empty] | Uptime (S) |  |  |  |  | Downtime (ALDT) |  |  |  | Total Time | Overall Total Time | Ao % | Mc %
|  | 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | F | Tf | FMC | PMC | MOD | Ms | Mr | L | A
M70-01 s/n: 6723 | F | [20 empty] | I | I | [35 empty] | 11 | 24 | 45.83% | 27.5% | bar: Uptime (S) F
Tf
FMC
| PMC | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | [26 empty] | Uptime (S) PMC: 11
MOD
| Ms | [57 empty] | 13
| Mr | [22 empty] | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Downtime (ALDT) Mr: 13
| L | [38 empty] | .
A
M70-02 s/n: 6737 | F | [57 empty] | 0 | 24 | 0% | 0%
Tf
FMC
PMC
MOD
| Ms | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Downtime (ALDT) Ms: 24 | 24
| Mr |  |  | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |  |  |  |  | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
L
A
M70-03 s/n: 6741 | F | [57 empty] | 0 | 24 | 0% | 0%
Tf
FMC
PMC
MOD
| Ms | [57 empty] | 24
Mr
L
| A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Downtime (ALDT) A: 24
[60 empty] | AVERAGE | 15.28% | 9.167%
Prepared by: | [12 empty] | NOTE: |  | M70-01 | [12 empty] | M70-02 | [14 empty] | M70-03 | [6 empty] | Downtime (ALDT) Ms: Verified by:
[15 empty] | 1. WMSA-WMSA : 1000H-1100H (1.0H) | [12 empty] | 1. NIL | [14 empty] | 1. NIL
Sign: | [49 empty] | Downtime (ALDT) Ms: Sign:
Name: | [49 empty] | Downtime (ALDT) Ms: Name:
Abbreviation
| F |  | Flying | [13 empty] | Ms |  |  | Maintenance schedule | [13 empty] | ALDT |  |  | Aircraft on ground / Maintenance down time
| Tf |  | Test flight | [13 empty] | Mr |  |  | Maintenance repair | [13 empty] | MOD |  |  | Modification / Service Bulletin
| FMC |  | Full Mission Capability | [13 empty] | L |  |  | Awaiting Maintenance
| PMC |  | Partial Mission Capability | [13 empty] | A |  |  | Awaiting Spare | [13 empty] | Formula
| S |  | Serviceable | [13 empty] | Ao |  |  | Operation Availability | [14 empty] | Ao = ∑FMC+[∑PMC] x 100 = _____ % | [14 empty] | Uptime (S) Tf: Mc = [(∑FMC)+0.6(∑PMC)] x 100 = ___ %
[36 empty] | 24 | [13 empty] | Uptime (S) FMC: 24
`
Tail No | Task / Defect Description | [40 empty] | Duration |  |  |  |  | Job No. |  |  | Downtime (ALDT) Ms: Remarks
M70-01 s/n: 6723 | 1 | SERVICEABLE (PMC) | [39 empty] | 11 | [7 empty] | Downtime (ALDT) Ms: LAST FLOWN 4/4/2024
| 2 | AIRCRAFT CONFIQ FROM SAR ROLE TO FERRY TANK INSTALLATION DUE TO CUSTOMER REQUIREMENT. | [39 empty] | 1 |  |  |  |  | UW/M70-01/24-023
| 3 | AIRCRAFT CONFIQ FROM TANK INSTALLATION TO SAR ROLE DUE TO CUSTOMER REQUIREMENT. | [39 empty] | 1 |  |  |  |  | UW/M70-01/24-024
| 4 | ACFT BANKING TO THE RIGHT PEDAL FULLY LEFT BALL FULLY RIGHT WHEN ENGAGE 'HDG'. | [39 empty] | 13 |  |  |  |  | UW/M70-01/24-025 |  |  | Downtime (ALDT) Ms: WIRING CHECK INPROGRESS
| 5 | FUEL INDICATOR #1 FLUCTUATE DURING T/OFF AND LANDING. | [39 empty] | 13 |  |  |  |  | UW/M70-01/24-026 |  |  | Downtime (ALDT) Ms: WIRING CHECK INPROGRESS
M70-02 s/n : 6737 | 1 | UNSERVICEABLE (MS) | [39 empty] | 24 | [7 empty] | Downtime (ALDT) Ms: LAST EGR 05/04/2024
| 2 | MAIN ROTOR TRACK AND BALANCE CX TO BE CARRIED OUT | [39 empty] | 24 |  |  |  |  | M70-02-5111 |  |  | Downtime (ALDT) Ms: AWAITING EGR
M70-03 s/n: 6741 | 1 | AWAITING SPARE (A) | [39 empty] | 24 | [7 empty] | Downtime (ALDT) Ms: LAST FLOWN 15/6/2023
|  | 1.ENGINE NO.1 & ENGINE NO.2 | [44 empty] | M70-03-3873
2.UPPER & LOWER ATTACHMENT BEAM
3.MAIN ROTOR BLADE (QTY:04)
4.MAIN GEAR BOX SUSPENSION BAR (QTY:1)
| 2 | 50H/100H/300H/400H/500H/600H/1200H/2400H/1M/3M/6M/24M/1Y/2Y/4Y INSPECTION IN PROGRES. | [39 empty] | 24
Prepared by:

## LAMPIRAN G-2
LAMPIRAN G-2
|  |  |  | Pesawat: | DAUPHINE | Tarikh: | 2024-04-09
|  |  |  | Aircraft: |  | Date:
|  |  |  | BAHAGIAN 2 - STATUS HARIAN PESAWAT | [15 empty] | Bahagian ini diisi oleh MC
|  |  | Part 2 - Daily Aircraft Status | [16 empty] | This parts to be filled by MC
Keadaan Pesawat pada jam 0800H
Aircraft State at 0800H
[7 empty] | Keadaan Semasa Current Status |  |  |  | Penangguhan Kerosakan (Jika ada) Deferred Defect (If any) |  |  |  | Rawatan Barisan Kedua Second Line Servicing
|  |  |  | Pesawat | Jam Enjin | Jam Pesawat | Keadaan | Tarikh Rosak | Butir Kerosakan | Jangka Masa Siap | Perkara | Tarikh Rosak | Jangka Masa Siap | Had Operasi (Jika ada) | Perkara | Tamat Pada Due at |  | Baki Balance |  | Catatan
|  |  |  | Tail Number | Eng TSN | A/C TSN | State | Date Unserviceable | Details of Unserviceable | Estimate | Description | Date Unserviceable | Estimate | Operational Limitation | Description | Jam Hrs | Kalendar Calendar | Jam Hrs | Hari Day | Remarks
TOTAL HOUR: | 7.1 |  |  | M70-01 ENG #1 S/N: 24401 ENG #2 S/N: 24422 | ENG #1: 1739.9 ENG #2: 1395.7 |  | Mr' MAINTENANCE REPAIR | 08 APR 2024 @ 1100H | 1.ACFT BANKING TO RIGHT ,PEDAL FULLY LEFT, BALL FULL RIGHT WHEN ENGAGE 'HDG'. 2. FUEL INDICATOR #1 FLUCTUATE DURING T/OFF AND LANDING. | 12 APR 2024 @ 2359H | DOPPLER RADAR INOPERATIVE (S/NO:377) | 26.06.2023 | EDD:28 DEC 2023 @ 2359H NEW REVISE EDD:28 APRIL 2024 @ 2359H | UNABLE FOR AUTO HOVER MODE | SCHEDULE INSPECTION |  |  |  |  | FLIR
1 | 0.9 | 17 | [12 empty] | 10H/7D | 4488.8 | 2024-04-15 | 10 | 6 | REMOVED
2 |  | 18 | [12 empty] | 20H | 4489.4 |  | 10.6
3 | 2.9 | 19 | [12 empty] | 25H/30H | 4483.2 |  | 4.4
4 | 2.3 | 20 | [12 empty] | 50H | 4508.2 |  | 29.4
5 |  | 21 | [12 empty] | 100H,100H/6M, | 4513.1 | 2024-06-05 | 34.3 | 57
6 |  | 22 | [12 empty] | 150H/300H/3M/6M | 4608.2 | 2024-05-20 | 129.4 | 41 | RESCUE HOIST
7 |  | 23 | [12 empty] | 300 HRS (AF, ENG #1 & #2) | 4499.6 |  | 20.8 |  | INSTALLED
8 | 1 | 24 | [12 empty] | 300H/2Y | 4758.2 | 2026-02-20 | 279.4 | 682
9 |  | 25 | [12 empty] | 400H/2Y | 4710 | 2025-07-17 | 231.2 | 464
10 |  | 26 | [12 empty] | 500H | 4656.5 |  | 177.7
11 |  | 27 | [12 empty] | 600H/1Y,1Y | 4515.2 | 2024-05-04 | 36.4 | 25
12 |  | 28 | [12 empty] | 600H,600H/2Y | 4515.2 | 2024-05-08 | 36.4 | 29 | LOUD HAILER
13 |  | 29 | [12 empty] | 1M ELT |  | 2024-05-05 |  | 26 | INSTALLED
14 |  | 30 | [12 empty] | 6M |  | 2024-08-21 |  | 134
15 |  | 31 |  |  | ENG #1 HRS | 4478.8 | [8 empty] | 1Y CVFDR |  | 2024-10-16 |  | 190
16 |  |  |  |  | 1960.9 | [9 empty] | FIRST AID KIT RECERTIFICATION |  | 2025-10-30 |  | 569
ENG #2 HRS
[5 empty] | 4959.7 | [9 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE
[15 empty] | EASB 01.00.71 REV 4/EASA AD No 2021-0170 (500H TGB) | 4737.8 |  | 259
[15 empty] | ASB 71.00.28 REV 0/ EASA AD No 2022-231 REV O (FIREWALL) | 4583.1 | 2024-10-25 | 104.3 | 199 | NIGHT SUN
[15 empty] | SB 80.00.03 REV 1 (STARTER GENERATOR #1) | 4553.5 |  | 74.7 |  | REMOVED
COMPONENT
[15 empty] | #1 ENGINE MODULE 03 SN:948 3500H TBO | 4569.2 |  | 90.4
[15 empty] | SPHERICAL THRUST BEARING BOLT QTY:06 | 4669.3 |  | 190.5 |  | CARGO HOOK
[15 empty] | MAIN ROTOR MAST HUB BOLT QTY:16 | 4915.2 |  | 436.4 |  | REMOVED
[15 empty] | 1Y CVFDR |  | 2024-10-13 |  | 187
FUEL
600
\
LAMPIRAN 1-B (Semakan 1)
|  |  |  | Pesawat: | DAUPHINE | Tarikh: | 2022-07-13
|  |  |  | Aircraft: |  | Date:
|  |  |  | BAHAGIAN 2 - STATUS HARIAN PESAWAT | [15 empty] | Bahagian ini diisi oleh MC
|  |  |  | Part 2 - Daily Aircraft Status | [15 empty] | This parts to be filled by MC
Keadaan Pesawat pada jam 0800H
Aircraft State at 0800H
[7 empty] | Keadaan Semasa Current Status |  |  |  | Penangguhan Kerosakan (Jika ada) Deferred Defect (If any) |  |  |  | Rawatan Barisan Kedua Second Line Servicing
|  |  |  | Pesawat | Jam Enjin | Jam Pesawat | Keadaan | Tarikh Rosak | Butir Kerosakan | Jangka Masa Siap | Perkara | Tarikh Rosak | Jangka Masa Siap | Had Operasi (Jika ada) | Perkara | Tamat Pada Due at |  | Baki Balance |  | Catatan
|  |  |  | Tail Number | Eng TSN | A/C TSN | State | Date Unserviceable | Details of Unserviceable | Estimate | Description | Date Unserviceable | Estimate | Operational Limitation | Description | Jam Hrs | Kalendar Calendar | Jam Hrs | Hari Day | Remarks
TOTAL HOUR: | 0 |  |  | M70-02 ENG #1 S/N: 24453 ENG #2 S/N: 24275 | ENG #1: 4742.6 ENG #2: 5446.1 |  | Ms' MAINTENANCE SCHEDULE | 04 APR 2024 @ 1510H | INSPECTION IN PROGRESS 1.MAIN ROTOR TRACK AND BALANCE CX 2. ENGINE EGR AND FLIGHT TEST | 05 APR 2024 @ 2359H NEW REVISED EDD: 12 APR 2024 @ 2359H. | DOPPLER RADAR INOPERATIVE (S/NO:423) | 07.10.2022 | EDD:10 MAC 2023 @ 2359H NEW REVISE EDD: 10 MEI 2024 @ 2359H | UNABLE FOR AUTO HOVER MODE | SCHEDULE INSPECTION |  |  |  |  | FLIR
1 |  | 17 | [12 empty] | 10H/7D | 4561.9 | 2024-04-11 | 10 | 2 | REMOVED
2 |  | 18 | [12 empty] | 20H | 4567.7 |  | 15.8
3 |  | 19 | [12 empty] | 25H/30H | 4576.9 |  | 25
4 |  | 20 | [12 empty] | 50H | 4589.1 |  | 37.2
5 |  | 21 | [12 empty] | 100H,100H/6M, | 4594.2 | 2024-08-23 | 42.3 | 136
6 |  | 22 | [12 empty] | 150H/300H/3M/6M | 4617.1 | 2024-05-06 | 65.2 | 27 | RESCUE HOIST
7 |  | 23 | [12 empty] | 300 HRS (AF, ENG #1 & #2) | 4794.2 |  | 242.3 |  | INSTALLED
8 |  | 24 | [12 empty] | 300H,300H/2Y | 4794.2 | 2026-02-23 | 242.3 | 685
9 |  | 25 | [12 empty] | 400H/2Y | 4618 | 2025-05-31 | 66.1 | 417
10 |  | 26 | [12 empty] | 500H | 4718 |  | 166.1
11 |  | 27 | [12 empty] | 600H/1Y,1Y | 4818 | 2024-05-31 | 266.1 | 52
12 |  | 28 | [12 empty] | 600H,600H/2Y | 4818 | 2025-05-31 | 266.1 | 417 | LOUD HAILER
13 |  | 29 | [12 empty] | 1M ELT |  | 2024-04-18 |  | 9 | INSTALLED
14 |  | 30 | [12 empty] | 6M |  | 2024-05-06 |  | 27
15 |  | 31 |  |  |  | 4551.9 | [8 empty] | FIRST AID KIT RECERTIFICATION |  | 2025-02-22 |  | 319
16 |  |  |  |  | ENG #1 HRS
4921.4
[5 empty] | ENG #2 HRS | [9 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE
[5 empty] | 5797.7 | [9 empty] | EASB 01.00.71 REV 4/EASA AD No 2021-0170 (500H TGB) | 5051.9 |  | 500
[15 empty] | SB 80.00.03 REV 1, #1 STARTER GENERATOR | 4852.3 |  | 300.4 |  | NIGHT SUN
REMOVED
[15 empty] | SB 05.00.81 R1 | 4818 |  | 266.1
COMPONENT
[15 empty] | MAIN ROTOR MAST HUB BOLT QTY:16 | 4726.4 |  | 174.5 |  | CARGO HOOK
REMOVED
[15 empty] | #1 STARTER GENERATOR (S/N 3048) | 4852.3 |  | 300.4
[15 empty] | 1 Y MAIN BATTERY |  | 2024-06-28 |  | 80
[15 empty] | 6M SOLID STATE CVFDR,CABIN FIREX |  | 2024-05-07 |  | 28 | FUEL
300
LAMPIRAN 1-B (Semakan 1)
|  |  |  | Pesawat: | DAUPHINE | Tarikh: | 2022-07-13
|  |  |  | Aircraft: |  | Date:
|  |  |  | BAHAGIAN 2 - STATUS HARIAN PESAWAT | [15 empty] | Bahagian ini diisi oleh MC
|  |  |  | Part 2 - Daily Aircraft Status | [15 empty] | This parts to be filled by MC
Keadaan Pesawat pada jam 0800H
Aircraft State at 0800H
[7 empty] | Keadaan Semasa Current Status |  |  |  | Penangguhan Kerosakan (Jika ada) Deferred Defect (If any) |  |  |  | Rawatan Barisan Kedua Second Line Servicing
|  |  |  | Pesawat | Jam Enjin | Jam Pesawat | Keadaan | Tarikh Rosak | Butir Kerosakan | Jangka Masa Siap | Perkara | Tarikh Rosak | Jangka Masa Siap | Had Operasi (Jika ada) | Perkara | Tamat Pada Due at |  | Baki Balance |  | Catatan
|  |  |  | Tail Number | Eng TSN | A/C TSN | State | Date Unserviceable | Details of Unserviceable | Estimate | Description | Date Unserviceable | Estimate | Operational Limitation | Description | Jam Hrs | Kalendar Calendar | Jam Hrs | Hari Day | Remarks
|  |  |  | M70-03 ENG #1 S/N: ENG #2 S/N: | ENG #1: 1709.3 ENG #2: 4535.3 |  | Ms' MAINTENANCE SCHEDULE | 16 Jun 2023 @ 1030H | 50H/100H/300H/400H/500H/600H/1200H/2400H/1M/3M/6M/24M/1Y/2Y/4Y INSPECTION IN PROGRES. AWAITING SPARE: 1). ENGINE NO.1 & ENGINE NO.2 2). UPPER & LOWER ATTACHMENT BEAM 3) MAIN ROTOR BLADE (QTY:04) 4) MAIN GEAR BOX SUSPENSION BAR (QTY:1) 5) LH HMU 10Y TBO (S/N: 1401B) | 24 OCT 2023 @ 2359H (AS PER CONTRACT ESTIMATE: 130 DAYS). NEW REVISE EDD: 09 MAY 2024 @ 2359H. | DOPPLER RADAR INOPERATIVE. (S/NO: 520) | 03.10.2022 | EDD: 06 MAC 2023 @ 2359H NEW REVISE EDD: 06 MEI 2024 @ 2359H. | UNABLE FOR AUTO HOVER MODE | SCHEDULE INSPECTION |  |  |  |  | FLIR
TOTAL HOUR: | 0 | [13 empty] | 10H/7D | 4452.5 | 2023-06-16 | 4.5 | -298 | REMOVED
1 |  | 17 | [12 empty] | 20H | 4449.4 |  | 1.4
2 |  | 18 | [12 empty] | 25H/30H | 4457.4 |  | 9.4
3 |  | 19 | [12 empty] | 50H | 4482.4 |  | 34.4
4 |  | 20 | [12 empty] | 100H,100H/6M, | 4494.3 | 2023-09-15 | 46.3 | -207
5 |  | 21 | [12 empty] | 150H/300H/3M/6M | 4646.7 | 2023-07-04 | 198.7 | -280 | RESCUE HOIST
6 |  | 22 | [12 empty] | 300 HRS (AF, ENG #1 & #2) | 4550.2 |  | 102.2 |  | REMOVED
7 |  | 23 | [12 empty] | 300H,300H/2Y | 4550.2 | 2023-06-30 | 102.2 | -284
8 |  | 24 | [12 empty] | 400H/2Y | 4604.8 | 2024-04-29 | 156.8 | 20
9 |  | 25 | [12 empty] | 500H | 4894.3 |  | 446.3
10 |  | 26 | [12 empty] | 600H/1Y,1Y | 4868.6 | 2023-10-07 | 420.6 | -185
11 |  | 27 | [12 empty] | 600H,600H/2Y | 4562.3 | 2023-07-01 | 114.3 | -283 | LOUD HAILER
12 |  | 28 | [12 empty] | 1M ELT |  | 2023-07-02 |  | -282 | REMOVED
13 |  | 29 | [12 empty] | 6M |  | 2023-11-15 |  | -146
14 |  | 30 |  |  | ENG #1 HRS | 4448 | [8 empty] | 1200 HRS / 4Y (CONCESSION) | 5162.3 | 2023-07-17 | 714.3 | -267
15 |  | 31 |  |  | 1895.2 | [9 empty] | 2400 HRS / 4Y (CONCESSION) | 5361.3 | 2023-07-17 | 913.3 | -267
16
ENG #2 HRS
[5 empty] | 4721.2 | [9 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE |  |  |  |  | NIGHT SUN
[15 empty] | EASB 01.00.71 REV 4/EASA AD No 2021-0170 (500H TGB) | 4462.3 |  | 14.3 |  | REMOVED
[15 empty] | ASB 25.01.91 R0/EASA AD No 2022-0220 REV 0 (SHEAR BUTTON) | 4461.4 |  | 13.4
[15 empty] | ASB 71.00.28 REV 0/ EASA AD No 2022-231 REV O (FIREWALL) | 4887.9 | 2024-10-25 | 439.9 | 199
[15 empty] | COMPONENT |  |  |  |  | CARGO HOOK
[15 empty] | BOOSTER PUMP S/N: C44910 2000H TBO | 4878.1 |  | 430.1
[15 empty] | BOOSTER PUMP S/N: A79760 2000H TBO | 4943.9 |  | 495.9
[15 empty] | ROTOR MAST-HUB ATTACHMENT BOLT 1000H SLL | 4952.5 |  | 504.5
[15 empty] | RH AFT FLOAT 1Y (S/N:3420) |  | 2024-01-30 |  | -70
[15 empty] | LH HMU 10Y TBO (S/N:1401B) |  | 2024-02-18 |  | -51 | FUEL
NIL
2
.
30