## LAMPIRAN G-1
LAMPIRAN G-1
OPERATIONAL AVAILABILITY SURVEILLANCE
Aircraft Type: |  |  |  | DAUPHINE AS365N3
Date: |  |  |  | 2024-09-29
Tail No |  | Time of the day | [47 empty] | Uptime (S) |  |  |  |  | Downtime (ALDT) |  |  |  | Total Time | Overall Total Time | Ao % | Mc %
|  | 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | F | Tf | FMC | PMC | MOD | Ms | Mr | L | A
M70-01 s/n: 6723 | F | [57 empty] | 0 | 24 | 0% | 0%
Tf
FMC
PMC
MOD
| Ms | [57 empty] | 24
Mr
| L | [38 empty] | .
| A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Downtime (ALDT) A: 24
M70-02 s/n: 6737 | F | [57 empty] | 24 | 24 | 100% | 60%
Tf
FMC
| PMC | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Uptime (S) PMC: 24
MOD
| Ms | [57 empty] | 0
Mr
L
A
M70-03 s/n: 6741 | F | [57 empty] | 0 | 24 | 0% | 0%
Tf
FMC
PMC
MOD
| Ms | [57 empty] | 24
Mr
L
| A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Downtime (ALDT) A: 24
[60 empty] | AVERAGE | 33.33% | 20%
Prepared by: | [12 empty] | NOTE: |  | M70-01 | [12 empty] | M70-02 | [14 empty] | M70-03 | [6 empty] | Downtime (ALDT) Ms: Verified by:
[15 empty] | 1. NIL | [12 empty] | 1. NIL | [14 empty] | 1. NIL
Sign: | [49 empty] | Downtime (ALDT) Ms: Sign:
Name: | [49 empty] | Downtime (ALDT) Ms: Name:
Abbreviation
| F |  | Flying | [13 empty] | Ms |  |  | Maintenance schedule | [13 empty] | ALDT |  |  | Aircraft on ground / Maintenance down time
| Tf |  | Test flight | [13 empty] | Mr |  |  | Maintenance repair | [13 empty] | MOD |  |  | Modification / Service Bulletin
| FMC |  | Full Mission Capability | [13 empty] | L |  |  | Awaiting Maintenance
| PMC |  | Partial Mission Capability | [13 empty] | A |  |  | Awaiting Spare | [13 empty] | Formula
| S |  | Serviceable | [13 empty] | Ao |  |  | Operation Availability | [14 empty] | Ao = ∑FMC+[∑PMC] x 100 = _____ % | [14 empty] | Uptime (S) Tf: Mc = [(∑FMC)+0.6(∑PMC)] x 100 = ___ %
[36 empty] | 24 | [13 empty] | Uptime (S) FMC: 24
`
Tail No | Task / Defect Description | [40 empty] | Duration |  |  |  |  | Job No. |  |  | Downtime (ALDT) Ms: Remarks
M70-01 s/n: 6723 | 1 | AWAITING SPARE (A) | [39 empty] | 24 | [7 empty] | Downtime (ALDT) Ms: LAST FLYING 07/5/2024
| 2 | 50H/100H/300H/400H/500H/600H/1200H/2400H/1M/3M/6M/24M/1Y/2Y/4Y INSPECTION IN PROGRES. | [39 empty] | 24 |  |  |  |  | M70-01-5160/5165/5166/5197/5198/5199
M70-02 s/n : 6737 | 1 | SERVICEABLE (PMC) | [39 empty] | 24 | [7 empty] | Downtime (ALDT) Ms: LAST FLYING 28/9/2024
M70-03 s/n: 6741 | 1 | AWAITING SPARE (A) | [39 empty] | 24 | [7 empty] | Downtime (ALDT) Ms: LAST EGR 27/9/2024
| 2 | ACFT VIBRATE IN FLIGHT | [39 empty] | 24 |  |  |  |  | UW/M70-03/24-103 |  |  | Downtime (ALDT) Ms: REQUIRED FLIGHT TEST
| 3 | GPS INTERMITTENT IN FLIGHT | [39 empty] | 24 |  |  |  |  | UW/M70-03/24-104 |  |  | Downtime (ALDT) Ms: REQUIRED AIR CHECK
Prepared by:

## LAMPIRAN G-2
LAMPIRAN G-2
[5 empty] | Pesawat: | DAUPHINE | Tarikh: | 2024-09-30
[5 empty] | Aircraft: |  | Date:
[5 empty] | BAHAGIAN 2 - STATUS HARIAN PESAWAT | [15 empty] | Bahagian ini diisi oleh MC
|  |  |  | Part 2 - Daily Aircraft Status | [16 empty] | This parts to be filled by MC
Keadaan Pesawat pada jam 0800H
Aircraft State at 0800H
[8 empty] | Keadaan Semasa Current Status |  |  |  | Penangguhan Kerosakan (Jika ada) Deferred Defect (If any) |  |  |  | Rawatan Barisan Kedua Second Line Servicing
[5 empty] | Pesawat | Jam Enjin | Jam Pesawat | Keadaan | Tarikh Rosak | Butir Kerosakan | Jangka Masa Siap | Perkara | Tarikh Rosak | Jangka Masa Siap | Had Operasi (Jika ada) | Perkara | Tamat Pada Due at |  | Baki Balance |  | Catatan
[5 empty] | Tail Number | Eng TSN | A/C TSN | State | Date Unserviceable | Details of Unserviceable | Estimate | Description | Date Unserviceable | Estimate | Operational Limitation | Description | Jam Hrs | Kalendar Calendar | Jam Hrs | Hari Day | Remarks
TOTAL HOUR: | 0 |  |  |  | M70-01 ENG #1 S/N: ENG #2 S/N: | ENG #1: 1739.9 ENG #2: 1395.7 |  | 'US' | 7 MEI 2024 @ 1800H | 50H/100H/300H/400H/500H/600H/1200H/2400H/1M/3M/6M/24M/1Y/2Y/4Y INSPECTION IN PROGRES. AWAITING SPARE: 1). UPPER & LOWER ATTACHMENT BEAM 2) LH HMU 10Y TBO (S/N: 1401B) | 14 SEPT 2024 @ 2359H (AS PER CONTRACT ESTIMATE: 130 DAYS). NEW REVISE EDD:31 JAN 2025 @ 2359H | DOPPLER RADAR INOPERATIVE (S/NO:377) | 26.06.2023 | EDD:28 DEC 2023 @ 2359H NEW REVISE EDD:28 SEPT 2024 @ 2359H | UNABLE FOR AUTO HOVER MODE | SCHEDULE INSPECTION |  |  |  |  | FLIR
1 |  | 17 | [13 empty] | 10H/7D | 4495.4 | 2024-05-07 | 7.5 | -146 | REMOVED
2 |  | 18 | [13 empty] | 20H | 4506.9 |  | 19
3 |  | 19 | [13 empty] | 25H/30H | 4505.8 |  | 17.9
4 |  | 20 | [13 empty] | 50H | 4508.2 |  | 20.3
5 |  | 21 | [13 empty] | 100H,100H/6M, | 4513.1 | 2024-06-05 | 25.2 | -117
6 |  | 22 | [13 empty] | 150H/300H/3M/6M | 4608.2 | 2024-05-20 | 120.3 | -133 | RESCUE HOIST
7 |  | 23 | [13 empty] | 300 HRS (AF, ENG #1 & #2) | 4499.6 |  | 11.7 |  | REMOVED
8 |  | 24 | [13 empty] | 300H/2Y | 4758.2 | 2026-02-20 | 270.3 | 508
9 |  | 25 | [13 empty] | 400H/2Y | 4710 | 2025-07-17 | 222.1 | 290
10 |  | 26 | [13 empty] | 500H | 4656.5 |  | 168.6
11 |  | 27
12 |  | 28 | [13 empty] | 600H,600H/2Y | 4515.2 | 2024-05-08 | 27.3 | -145 | LOUD HAILER
13 |  | 29 | [13 empty] | 1M ELT |  | 2024-06-03 |  | -119 | REMOVED
14 |  | 30 | [13 empty] | 6M |  | 2024-08-21 |  | -40
15 |  | 31 |  |  |  | ENG #1 HRS | 4487.9 | [8 empty] | 1Y CVFDR |  | 2024-10-16 |  | 16
16 | [15 empty] | FIRST AID KIT RECERTIFICATION |  | 2025-10-30 |  | 395
ENG #2 HRS
SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE
[16 empty] | EASB 01.00.71 REV 4/EASA AD No 2021-0170 (500H TGB) | 4737.8 |  | 249.9
[16 empty] | ASB 71.00.28 REV 0/ EASA AD No 2022-231 REV O (FIREWALL) | 4583.1 | 2024-10-25 | 95.2 | 25 | NIGHT SUN
[16 empty] | SB 80.00.03 REV 1 (STARTER GENERATOR #1) | 4553.5 |  | 65.6 |  | REMOVED
COMPONENT
[16 empty] | SPHERICAL THRUST BEARING BOLT QTY:06 | 4669.3 |  | 181.4 |  | CARGO HOOK
[16 empty] | MAIN ROTOR MAST HUB BOLT QTY:16 | 4915.2 |  | 427.3 |  | REMOVED
[16 empty] | 1Y CVFDR |  | 2024-10-13 |  | 13
FUEL
0
\
LAMPIRAN 1-B (Semakan 1)
[5 empty] | Pesawat: | DAUPHINE | Tarikh: | 2022-07-13
[5 empty] | Aircraft: |  | Date:
[5 empty] | BAHAGIAN 2 - STATUS HARIAN PESAWAT | [15 empty] | Bahagian ini diisi oleh MC
[5 empty] | Part 2 - Daily Aircraft Status | [15 empty] | This parts to be filled by MC
Keadaan Pesawat pada jam 0800H
Aircraft State at 0800H
[8 empty] | Keadaan Semasa Current Status |  |  |  | Penangguhan Kerosakan (Jika ada) Deferred Defect (If any) |  |  |  | Rawatan Barisan Kedua Second Line Servicing
[5 empty] | Pesawat | Jam Enjin | Jam Pesawat | Keadaan | Tarikh Rosak | Butir Kerosakan | Jangka Masa Siap | Perkara | Tarikh Rosak | Jangka Masa Siap | Had Operasi (Jika ada) | Perkara | Tamat Pada Due at |  | Baki Balance |  | Catatan
[5 empty] | Tail Number | Eng TSN | A/C TSN | State | Date Unserviceable | Details of Unserviceable | Estimate | Description | Date Unserviceable | Estimate | Operational Limitation | Description | Jam Hrs | Kalendar Calendar | Jam Hrs | Hari Day | Remarks
TOTAL HOUR: | 37.4 |  |  |  | M70-02 ENG #1 S/N: 24453 ENG #2 S/N: 24275 | ENG #1: 4742.6 ENG #2: 5446.1 |  | S |  |  |  | DOPPLER RADAR INOPERATIVE (S/NO:423) | 07.10.2022 | EDD:10 MAC 2023 @ 2359H NEW REVISE EDD: 10 OCT 2024 @ 2359H | UNABLE FOR AUTO HOVER MODE | SCHEDULE INSPECTION |  |  |  |  | FLIR
1 | 2 | 17 | 2 | [12 empty] | 10H/7D | 4780 | 2024-10-05 | 10 | 5 | REMOVED
2 | 3 | 18 | 2.2 | [12 empty] | 20H | 4785.3 |  | 15.3
3 |  | 19 | 2 | [12 empty] | 25H/30H | 4779.9 |  | 9.9
4 | 1.5 | 20 | 0.6 | [12 empty] | 50H | 4804.9 |  | 34.9
5 | 0.6 | 21 | [13 empty] | 100H,100H/6M, | 4854.9 | 2024-11-05 | 84.9 | 36
6 | 2.5 | 22 | [13 empty] | 150H/300H/3M/6M | 4861 | 2024-10-31 | 91 | 31 | RESCUE HOIST
7 |  | 23 | [13 empty] | 300 HRS (AF, ENG #1 & #2) | 4794.2 |  | 24.2 |  | INSTALLED
8 |  | 24 | 1.1 | [12 empty] | 300H,300H/2Y | 4794.2 | 2026-02-23 | 24.2 | 511
9 | 4.1 | 25 | 1.3 | [12 empty] | 400H/2Y | 4976.7 | 2026-05-05 | 206.7 | 582
10 |  | 26 | 4.3 | [12 empty] | 500H | 5211 |  | 441
11 | 1.5 | 27 | 3.7 | [12 empty] | 600H/1Y,1Y | 5176.7 | 2025-05-05 | 406.7 | 217
12 |  | 28 | 4.7 | [12 empty] | 600H,600H/2Y | 4818 | 2025-05-15 | 48 | 227 | LOUD HAILER
13 |  | 29 | [13 empty] | 1200, 1200/2Y | 5418 | 2025-05-15 | 648 | 227 | INSTALLED
14 | 0.3 | 30
15 |  | 31 |  |  |  |  | 4770
16 | [5 empty] | ENG #1 HRS
5139.5
[6 empty] | ENG #2 HRS | [9 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE
[6 empty] | 6015.8 | [9 empty] | EASB 01.00.71 REV 4/EASA AD No 2021-0170 (500H TGB) | 5051.9 |  | 281.9
[16 empty] | SB 80.00.03 REV 1, #1 STARTER GENERATOR | 4852.3 |  | 82.3 |  | NIGHT SUN
[16 empty] | SB 05.00.81 R1 | 4818 |  | 48 |  | REMOVED
COMPONENT
[16 empty] | 6M MAIN BATTERY S/N: N01646 |  | 2024-10-18 |  | 18
[16 empty] | BOOSTER PUMP S/N: A79752 2000H TBO | 5195.6 |  | 425.6 |  | CARGO HOOK
[16 empty] | ANTENNA DRIVE S/N: T2128 3000FH/3Y TBO |  | 2025-03-29 |  | 180 | REMOVED
[16 empty] | #1 STARTER GENERATOR (S/N 3048) | 4852.3 |  | 82.3
[16 empty] | 1 Y MAIN BATTERY |  | 2025-04-18 |  | 200
[16 empty] | 6M SOLID STATE CVFDR,CABIN FIREX |  | 2024-11-05 |  | 36 | FUEL
[16 empty] | LH AFT FLOAT S/N: |  |  |  |  | 850
LAMPIRAN 1-B (Semakan 1)
[5 empty] | Pesawat: | DAUPHINE | Tarikh: | 2022-07-13
[5 empty] | Aircraft: |  | Date:
[5 empty] | BAHAGIAN 2 - STATUS HARIAN PESAWAT | [15 empty] | Bahagian ini diisi oleh MC
[5 empty] | Part 2 - Daily Aircraft Status | [15 empty] | This parts to be filled by MC
Keadaan Pesawat pada jam 0800H
Aircraft State at 0800H
[8 empty] | Keadaan Semasa Current Status |  |  |  | Penangguhan Kerosakan (Jika ada) Deferred Defect (If any) |  |  |  | Rawatan Barisan Kedua Second Line Servicing
[5 empty] | Pesawat | Jam Enjin | Jam Pesawat | Keadaan | Tarikh Rosak | Butir Kerosakan | Jangka Masa Siap | Perkara | Tarikh Rosak | Jangka Masa Siap | Had Operasi (Jika ada) | Perkara | Tamat Pada Due at |  | Baki Balance |  | Catatan
[5 empty] | Tail Number | Eng TSN | A/C TSN | State | Date Unserviceable | Details of Unserviceable | Estimate | Description | Date Unserviceable | Estimate | Operational Limitation | Description | Jam Hrs | Kalendar Calendar | Jam Hrs | Hari Day | Remarks
[5 empty] | M70-03 ENG #1 S/N: 24125 ENG #2 S/N: 24422 | ENG #1: 1709.3 ENG #2: 4535.3 |  | 'US' | 20 SEP 2024 @ 1154H | 1. ACFT VIBRATE IN FLIGHT 2. GPS INTERMITTENT IN FLIGHT 3. LH AFT FLOAT ASSY REMOVED TO SERVICE M70-02 (DUE 1YEAR INSPECTION) | 23 SEP 2024 @ 2359H NEW REVISE 2 OCT 2024 @2359H 24 SEP 2024 @ 2359H NEW REVISE 2 OCT 2024 @2359H 27 SEP 2024 @ 2359H NEW REVISE 2 OCT 2024 @2359H | DOPPLER RADAR INOPERATIVE. (S/NO: 520) | 03.10.2022 | EDD: 06 MAC 2023 @ 2359H NEW REVISE EDD: 06 OCT 2024 @ 2359H. | UNABLE FOR AUTO HOVER MODE | SCHEDULE INSPECTION |  |  |  |  | FLIR
TOTAL HOUR: | 14.1 | [14 empty] | 10H/7D | 4521.8 | 2024-10-02 | 10 | 2 | REMOVED
1 |  | 17 | [13 empty] | 20H | 4525 |  | 13.2
2 |  | 18 | [13 empty] | 25H/30H | 4536.2 |  | 24.4
3 | 2.4 | 19 | [13 empty] | 50H | 4538.9 |  | 27.1
4 | 1.8 | 20 | 1.4 | [12 empty] | 100H,100H/6M, | 4548 | 2024-12-23 | 36.2 | 84
5 | 1.8 | 21 | 0.6 | [12 empty] | 150H/300H/3M/6M | 4659.8 | 2024-12-17 | 148 | 78 | RESCUE HOIST
6 |  | 22 | [13 empty] | 300 HRS (AF ENG #1) | 4809.8 |  | 298 |  | INSTALLED
7 |  | 23 | [13 empty] | 300 HRS (AF ENG #2) | 4809.8 |  | 298
8 |  | 24 | [13 empty] | 300H,300H/2Y | 4748 | 2026-06-23 | 236.2 | 631
9 | 1.3 | 25 | [13 empty] | 400H/2Y | 4848 | 2026-06-23 | 336.2 | 631
10 |  | 26 | [13 empty] | 500H | 4948 |  | 436.2
11 | 0.5 | 27 |  |  |  | ENG #1 HRS | [9 empty] | 600H/1Y,1Y | 5048 | 2025-06-23 | 536.2 | 266 | LOUD HAILER
12 | 2.3 | 28 |  |  |  | 5262.5 | [9 empty] | 600H,600H/2Y | 5048 | 2026-06-23 | 536.2 | 631 | INSTALLED
13 | 2 | 29 |  |  |  |  | 4511.8 | [8 empty] | 1M ELT |  | 2024-10-20 |  | 20
14 |  | 30 |  |  |  | ENG #2 HRS | [9 empty] | 6M |  | 2024-12-23 |  | 84
15 |  | 31 |  |  |  | 5032.6 | [9 empty] | 1200 HRS / 4Y | 5648 | 2028-06-23 | 1136.2 | 1362
16 | [15 empty] | 2400 HRS / 4Y | 6848 | 2028-06-23 | 2336.2 | 1362
[16 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE |  |  |  |  | NIGHT SUN
[16 empty] | EASB 01.00.71 REV 4/EASA AD No 2021-0170 (500H TGB) | 4948 |  | 436.2 |  | REMOVED
[16 empty] | COMPONENT |  |  |  |  | CARGO HOOK
[16 empty] | BOOSTER PUMP S/N: C44910 2000H TBO | 4878.1 |  | 366.3
[16 empty] | BOOSTER PUMP S/N: A79760 2000H TBO | 4943.9 |  | 432.1 |  | FUEL
[16 empty] | STARTER GENERATOR S/N:5421 | 4973.2 |  | 461.4
[16 empty] | #2 ENGINE MODULE 04 SN:1802 3500H TBO | 4818.5 |  | 306.7
[16 empty] | 6M SOLID STATE CVFDR S/N: ARCOMBI-12091 |  | 2024-12-03 |  | 64
[16 empty] | 6M MAIN BATTERY S/N: X1531 |  | 2024-11-13 |  | 44
[16 empty] | 1Y MAIN BATTERY S/N: X1531 |  | 2024-12-28 |  | 89
[16 empty] | ROTOR MAST-HUB ATTACHMENT BOLT 1000H SLL | 4952.5 |  | 440.7 |  | 600
2
.
30