## LAMPIRAN 1 - A
LAMPIRAN 1-A
OPERATIONAL AVAILABILITY SURVEILLANCE
Aircraft Type: |  |  |  | AW 139
Date: |  |  |  | 2023-10-24
Tail No |  | Time of the day | [47 empty] | Uptime (S) |  |  |  |  | Downtime (ALDT) |  |  |  | Total Time | Overall Total Time | Ao %
|  | 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | F | Tf | FMC | PMC | MOD | Ms | Mr | L | A
M72-01 s/n: 31307 | F | [18 empty] | I | I | I | [36 empty] | 23 | 24 | 95.8333 | bar: Uptime (S) F
Tf
| FMC | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |  | I | I | I | I | I | I | I | I | I | I | I | [17 empty] | Uptime (S) FMC: 14.5
| PMC | [33 empty] | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Uptime (S) PMC: 7.5
MOD
| Ms | [57 empty] | 1
| Mr | [31 empty] | I | I | bar: Downtime (ALDT) Mr
L
A
M72-02 s/n: 31315 | F | [18 empty] | I | I | I | [19 empty] | I | I | I |  | I | I | I |  | Uptime (S) F: 4.5 | 23 | 24 | 95.8333
Tf
| FMC | [35 empty] | I | I | I | I | I |  |  |  | I |  |  |  | I | Uptime (S) PMC: 3.5
| PMC | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |  |  |  | I | I | I | I | I | I | I | I | I | I | I | I | [15 empty] | Uptime (S) FMC: 15
MOD
| Ms | [57 empty] | 1
| Mr | [33 empty] | I | I | bar: Downtime (ALDT) Mr
L
A
M72-03 s/n: 31316 | F | [57 empty] | 0 | 24 | 0
Tf
FMC
PMC
MOD
| Ms | [57 empty] | 24
| Mr | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | Downtime (ALDT) Mr: 24
L
A
[60 empty] | AVERAGE | 95.8333
Prepared by: | [21 empty] | NOTES: | [27 empty] | Uptime (S) MOD: Verified by:
M72-01:VIB CX WMSA - WMSA (0908 - 1008 = 1.0)
Sign: | [49 empty] | Uptime (S) MOD: Sign:
Name: | [21 empty] | M72-02:PHX 24 (WMSA-WMSA)0900-1030=1.5, PHX 23 (WMSA-WMSA)2000-2130=1.5, PHX 23(WMSA-WMSA)2200-2330=1.5 | [27 empty] | Uptime (S) MOD: Name:
M72-03:U/S DUE TO BOTH SPONSON CORROSION
Abbreviation
| F |  | Flying | [13 empty] | Ms |  |  | Maintenance schedule | [13 empty] | ALDT |  |  | Aircraft on ground / Maintenance down time
| Tf |  | Test flight | [13 empty] | Mr |  |  | Maintenance repair | [13 empty] | MOD |  |  | Modification / Service Bulletin
| FMC |  | Full Mission Capability | [13 empty] | L |  |  | Awaiting Maintenance
| PMC |  | Partial Mission Capability | [13 empty] | A |  |  | Awaiting Spare
| S |  | Serviceable | [13 empty] | Ao |  |  | Operation Availability
Tail No | Task / Defect Description | [40 empty] | Duration |  |  |  |  | Job No.
M72-01 s/n: 31307 | 1 | SERVICEABLE (PMC) | [39 empty] | 23 | [7 empty] | Downtime (ALDT) Ms: LAST FLOWN 23/10/2023
| 2 | MR & TR Vibration Cx (50 hrs) | [39 empty] | 1 |  |  |  |  | 2023-4502
| 3 | FLIR REMOVE TO SERVICE DUE TO OPERATIONAL REQUIREMENT | [39 empty] | 1 |  |  |  |  | UW/M72-01/23-069
| 4 | 25 HRS INSP | [39 empty] | 0 |  |  |  |  | 4473-001
5
6
7
8
9
10
11
M72-02 s/n: 31315 | 1 | SERVICEABLE (FMC) | [39 empty] | 23 | [7 empty] | Downtime (ALDT) Ms: LAST FLOWN 23/10/2023
| 2 | FLIR INSTALLATION | [39 empty] | 1 |  |  |  |  | UW/M72-02/23-084
3
4
5
6
7
8
9
10
M72-03 s/n: 31316 | 1 | UNSERVICEABLE (U/S) | [39 empty] | 0 | [7 empty] | Downtime (ALDT) Ms: LAST FLOWN 06/06/2022
| 2 | BOTH SPONSON STUCTURE FORWARD SEGMEN FOUND CORROSION | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | [5 empty] | UW/M72-03/22-084
| 3 | AIRCRAFT SENT TO LHM | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE | BOTH SPONSON STUCTURE
| 4 | CARRIED OUT PRE-INSPECTION BEFORE REPLACEMENT OF FRAME STA5700
| 5 | AIRCOND COMPRESSOR PACK ASSY ROB TO SERVICE M72-01 | [44 empty] | UW/M72-03/23-001
| 6 | PILOT SIDE R/H FORCE TRIM MICROSWITCH REMOVED TO SERVICE M72-02 | [44 empty] | UW/M72-03/23-002
| 7 | CABIN EVAPORATOR ASSY ROB TO SERVICE M72-01 | [44 empty] | UW/M72-03/23-003
| 8 | NO 1 AND NO 2 STARTER GENERATOR REMOVED TO SERVICE M72-02 | [44 empty] | UW/M72-03/23-004
| 9 | CENTRAL DISPLAY UNIT REMOVED TO SERVICED M72-01. | [44 empty] | UW/M72-03/23-005
| 10 | RH WHEEL HUB ASSY ROB TO SERVICE M72-01 | [44 empty] | UW/M72-03/23-006
| 11 | BOTH ENGINE REMOVED TO SERVICE M72-01 | [44 empty] | UW/M72-03/23-007
| 12 | NOSE WHEEL CENTRE LOCK REMOVED TO SERVICE M72-02 | [44 empty] | UW/M72-03/23-013
Prepared by:

## LAMPIRAN 1 - B
LAMPIRAN 1-B (Semakan 1)
Pesawat: | AW139 | Tarikh: | 2023-10-25
Aircraft: |  | Date:
BAHAGIAN 2 - STATUS HARIAN PESAWAT | [15 empty] | Bahagian ini diisi oleh MC
Part 2 - Daily Aircraft Status | [15 empty] | This parts to be filled by MC
Keadaan Pesawat pada jam 0800H
Aircraft State at 0800H
|  |  | Keadaan Semasa Current Status |  |  |  | Penangguhan Kerosakan (Jika ada) Deferred Defect (If any) |  |  |  | Rawatan Barisan Kedua Second Line Servicing
Pesawat | Jam Enjin | Jam Pesawat | Keadaan | Tarikh Rosak | Butir Kerosakan | Jangka Masa Siap | Perkara | Tarikh Rosak | Jangka Masa Siap | Had Operasi (Jika ada) | Perkara | Tamat Pada Due at |  | Baki Balance |  | Catatan
Tail Number | Eng TSN | A/C TSN | State | Date Unserviceable | Details of Unserviceable | Estimate | Description | Date Unserviceable | Estimate | Operational Limitation | Description | Jam Hrs | Kalendar Calendar | Jam Hrs | Hari Day | Remarks
|  | 4829 | " S " PMC | [7 empty] | SCHEDULE INSPECTION
[11 empty] | 25 Hrs Insp | 4854 |  | 25 |  | SEAT CONFIGURATION
[11 empty] | 50 Hrs Insp | 4840.1 |  | 11.1 |  | TROOP SEATS
[11 empty] | 100 Hrs Insp | 4890.1 |  | 61.1 |  | INSTALLED
[11 empty] | 150 Hrs Insp | 4931.1 |  | 102.1
[11 empty] | 1 Mth Insp. HOIST |  | 2023-11-06 |  | 12 | FLIR
[11 empty] | 3 Mth Insp |  | 2023-10-26 |  | 1 | INSTALLED
[11 empty] | 6 Mnth. Insp. |  | 2023-12-15 |  | 51 | CEU SER NO: 3421282
[11 empty] | 1 Mth FLIR Purging |  | 2023-10-28 |  | 3 | TFU SER NO: 3411282
[11 empty] | FMS NAV Data Update |  | 2023-11-01 |  | 7 | HCU SER NO: 3431282
[11 empty] | 50 Hrs / 2 Mth | 4840.1 | 2023-11-21 | 11.1 | 27 | LOUD HAILER
M72-01 | [10 empty] | 3 Mth Anti-Microbial Additives Application |  | 2023-12-14 |  | 50 | INSTALLED
31307 | [10 empty] | 120 Days Insp |  | 2024-02-05 |  | 103
[11 empty] | Main Battery (Cap Cx) S/N: 12100162 |  | 2024-03-13 |  | 140
[11 empty] | Aux Battery (Cap Cx) S/N: 10601367 |  | 2024-03-13 |  | 140 | RESCUE HOIST
[11 empty] | MR & TR Vibration Cx (50 hrs) | 4879 |  | 50 |  | INSTALLED
[11 empty] | 150 Hrs / 1 Y Insp | 4931.1 | 2024-09-18 | 102.1 | 329 | SER NO: 40077
ENG #1 | [10 empty] | 300 Hrs / 6 Month Insp | 5090.1 | 2024-03-21 | 261.1 | 148 | OPS HRS: 30.5
PCE- | [10 empty] | 200 Hrs Insp | 4967.7 |  | 138.7 |  | CART. SER NO: 12424
KB0742 | [10 empty] | Pitch Link Play Check (150 FH Reduced to 100 FH) | 4898.8 |  | 69.8 |  | 6 MTH CX: 13/03/2024
| ENG #1 | [9 empty] | 300 Inspection | 4961.8 |  | 132.8
| 3215.1 | [9 empty] | 300 Hrs / 1 Year Insp | 5128 | 2024-10-21 | 299 | 362
[11 empty] | 1 Year Inspection |  | 2023-12-16 |  | 52
[11 empty] | 900 FH / 1 Y Inspection | 5276.5 | 2023-12-16 | 447.5 | 52 | CARGO HOOK
[11 empty] | 450 FH - Hoist Inspection | 4902.1 |  | 73.1
[11 empty] | 1200 FH / 1 Y Inspection | 5576.5 | 2023-12-16 | 747.5 | 52 | REMOVED
[7 empty] | FLIR NOT FITTED | 24.10.23 | 25.12.23 |  | CORROSION CONTROL PROGRAMME (CCP)
[11 empty] | 7 Day CCP |  | 2023-10-28 |  | 3
[11 empty] | 1 Mth CCP |  | 2023-11-06 |  | 12 | FLOATATION SYS
[11 empty] | 3 Mth CCP |  | 2023-12-14 |  | 50 | INSTALLED
[11 empty] | 6 Mth CCP |  | 2024-03-21 |  | 148 | SER NO: 249 , 235 , 139 , 139
ANN. INSP: 26/12/2023
ENG #2 | ENG #2
PCE- | 3175 | [9 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE |  |  |  |  | LIFE RAFT
KB0739 | [10 empty] | ASB139-654 (Part II) - Main Rotor Swashplate Boot Insp - EVERY 50FH | 4840.1 |  | 11.1 |  | INSTALLED
[11 empty] | ASB139-724 REV B - TR Damper Bracket Insp. EVERY 50FH/6M | 4840.1 | 2024-03-21 | 11.1 | 148 | SER NO: 232 , 206
[11 empty] | SB139-728 TR Duplex Bearing Insp (Part I) - EVERY 50FH | 4840.1 |  | 11.1 |  | ANN. INSP: 26/1/2024
[11 empty] | SB139-661 REV. B PART II - Overhead Panel Insp | 4961.8 | 2024-03-21 | 132.8 | 148
[11 empty] | COMPONENT | SERVICING / ANNUAL |  | O/HAUL |  | AC LANDING CYCLE
[11 empty] | Main Rotor Actuator Replacement due 4500 Airframe Hrs (OV) S/N: HSC222303 | 4855.5 |  | 26.5 |  | 5418
[11 empty] | Emergency Float Annual |  | 2023-12-26 |  | 62 | FUEL
[11 empty] | Main Gearbox Assy Overhaul, SN:V14 | 5000 |  | 171 |  | 1044 kg
[11 empty] | Lubricating Pump Replacement, SN: 0809,0810 | 5000 |  | 171
[11 empty] | TR Elastomeric Spherical Bearing Replacement, SN: 1053,1052,1054,1055 | 5000 |  | 171
[11 empty] | Annual LH & RH Liferaft |  | 2024-01-26 |  | 93
[11 empty] | Bearing Support Assy Replacement, SN: TBK0044 | 5000 |  | 171
[11 empty] | Input Shaft Replacement, SN: 0828,0841 | 5000 |  | 171
|  | 4551.8 | " S " FMC | [7 empty] | SCHEDULE INSPECTION | [5 empty] | #REF!
SEAT CONFIGURATION
[11 empty] | 25 Hrs Insp | 4563.2 |  | 11.4 |  | TROOP SEATS
[11 empty] | 50 Hrs Insp | 4594.6 |  | 42.8 |  | INSTALLED
[11 empty] | 100 Hrs Insp | 4599.6 |  | 47.8 |  | FLIR
[11 empty] | 150 Hrs Insp | 4628.2 |  | 76.4 |  | REMOVED
[11 empty] | 1 Mth Insp. Hoist |  | 2023-11-22 |  | 28 | CEU SER NO: 3421282
[11 empty] | 3 Mth Insp HOIST |  | 2023-12-23 |  | 59 | TFU SER NO: 3411282
[11 empty] | 6 Mth Insp. |  | 2024-02-01 |  | 99 | HCU SER NO: 3431282
[11 empty] | FMS Nav Data Updates |  | 2023-11-01 |  | 7
[11 empty] | 1 Mth FLIR Purging |  | N/A |  | N/A |  | 99
[11 empty] | 50Hrs / 2 Mths Insp | 4594.6 | 2023-11-02 | 42.8 | 8
[11 empty] | 120 Days Insp |  | 2023-11-09 |  | 15 | RESCUE HOIST
M72-02 | [10 empty] | 3 Mth Anti-Microbial Additives Application |  | 2023-11-10 |  | 16 | INSTALLED
31315 | [10 empty] | Main Battery (Cap Cx) S/N: 11903005 |  | 2024-02-01 |  | 99 | SER NO: 40096
[11 empty] | Aux Battery (Cap Cx) S/N: 10900402 |  | 2024-02-01 |  | 99 | OPS HRS: 71.3
[11 empty] | MR & TR Vibration Cx - 50 hrs | 4594.6 |  | 42.8 |  | CART. SER NO: 13750
ENG #1 | ENG #1 | [9 empty] | 150 Hrs / 1 Y Insp | 4628.2 | 2024-08-04 | 76.4 | 284 | 6 MTH CX: 14/12/2023
| 4551.8 | [9 empty] | 200 Hrs Insp | 4699.6 |  | 147.8
PCE- | [10 empty] | 300 Hrs Insp | 4799.6 |  | 247.8
KB0740 | [10 empty] | MVA Torque Cx (After 25FH from bolts retorque) | 4558.6 |  | 6.8
[11 empty] | FWD Bulkhead Installation | 4557.3 | 2024-03-13 | 5.5 | 140
[11 empty] | 300 Hrs / 6 Month Insp | 4730.4 | 2023-12-08 | 178.6 | 44
CARGO HOOK
REMOVED
FLOATATION SYS
INSTALLED
S/N:
ENG #2 | ENG #2 | [9 empty] | CORROSION CONTROL PROGRAMME (CCP) |  |  |  |  | S/N ; 247, 240, 132, 107
PCE- | 4551.8 | [9 empty] | 7 Day CCP |  | 2023-10-27 |  | 2
KB0732 | [10 empty] | 1 Mth CCP |  | 2023-11-22 |  | 28 | ANN. INSP : 23/3/2024
[11 empty] | 3 Mth CCP |  | 2024-01-10 |  | 77
[11 empty] | 6 Mth CCP |  | 2024-02-01 |  | 99 | LIFE RAFT
[11 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE |  |  |  |  | INSTALLED
[11 empty] | ASB139-654 (Part II) - Main Rotor Swashplate Boot Insp - EVERY 50FH | 4594.6 |  | 42.8 |  | S/N: 229, 236
[11 empty] | ASB139-724 REV B - TR Damper Bracket Insp. EVERY 50FH/6M | 4594.6 | 2024-03-23 | 42.8 | 150 | ANN. INSP : 9/5/2024
[11 empty] | SB139-728 TR Duplex Bearing Insp (Part I) - EVERY 50FH | 4594.6 |  | 42.8 |  | LOUD HAILER
[11 empty] | SB139-728 TR Duplex Bearing Insp (Part II) | 4599.6 |  | 47.8
[11 empty] | SB139-728 TR Duplex Bearing Insp (Part III) | 4644.5 |  | 92.7 |  | NIL
[11 empty] | COMPONENT | SERVICING / ANNUAL |  | O/HAUL |  | AC LANDING CYCLE
[11 empty] | Float Annual Insp |  | 2024-03-23 |  | 150 | 5138
FUEL
1042kg
\
|  | 2803.8 | 'US' | [7 empty] | SCHEDULE INSPECTION | [5 empty] | #REF!
SEAT CONFIGURATION
[11 empty] | 25 Hrs Insp | 2825.5 |  | 21.7 |  | TROOP SEATS
[11 empty] | 50 Hrs Insp | 2815.9 |  | 12.1 |  | INSTALLED | #REF!
[11 empty] | 100 Hrs Insp | 2836.2 |  | 32.4
[11 empty] | 150 Hrs Insp. | 2849.1 |  | 45.3 |  | FLIR
[11 empty] | 1 Mth Insp HOIST |  | 2022-10-15 |  | -375 | REMOVED
[11 empty] | 3 Mth Insp |  | 2022-10-15 |  | -375 | TFU S/N: 3411283
[11 empty] | 6 Mth. Insp. |  | 2022-10-28 |  | -362 | CEU S/N: 3411283
M72-03 | [10 empty] | FMS Nav Data Updates |  | 2022-11-02 |  | -357
31316 | [10 empty] | 1 Mth FLIR Purging |  | N/A |  | N/A | RESCUE HOIST
[16 empty] | REMOVED | -375
SER NO : 40096
[11 empty] | 50Hrs / 2 Mths Insp | 2834.7 | 2022-11-08 | 30.9 | -351 | OPS HOURS : 66.9
[11 empty] | 120 Days Insp |  | 2022-12-10 |  | -319 | CART SER NO:11201
[11 empty] | 3 Mth Anti-Microbial Additives Application |  | 2022-10-28 |  | -362
[11 empty] | Pitch Link Play Check (150 FH Reduced to 100 FH) | 2836.2 |  | 32.4 |  | 6 MONTH CX: 20/12/2023
ENG #1 | ENG #1 | [9 empty] | Main Battery (Cap CX) S/N: 11000779 |  | 2022-10-22 |  | -368
[11 empty] | Aux Battery (Cap Cx) S/N:10802955 |  | 2022-10-22 |  | -368 | LOUD HAILER
NIL | NIL | [9 empty] | 402 Hrs Insp | 2869.6 |  | 65.8 |  | INSTALLED
[11 empty] | MR & TR Vibration Cx (50 hrs) | 2830.5 |  | 26.7
[11 empty] | 200 Hrs Insp | 2848.6 |  | 44.8
[11 empty] | 600 Hrs Insp | 2857.8 |  | 54 |  | CARGO HOOK
[11 empty] | 600 Hrs Insp #ENG 1 | 2857.8 |  | #VALUE!
|  |  |  | 2022-10-12 | 4 YEARS INSPECTION. | [5 empty] | 4 Y Insp |  | 2022-10-20 |  | -370 | REMOVED
[11 empty] | 150 Hrs / 1 Y Insp | 2886.2 | 2023-06-07 | 82.4 | -140
[5 empty] | BOTH SPONSON STUCTURE | 2023-06-27 |  |  |  |  | 300 Hrs / 6 Mth Insp | 3007 | 2022-10-28 | 203.2 | -362 | SQUIB S/NO: NIL
[5 empty] | FORWARD SEGMEN | [5 empty] | 4450 Landing | 4450 |  | 104 |  | HOOK S/NO: NIL
[5 empty] | FOUND CORROSION | NEW REVISE
EDD:
[5 empty] | AC HAS BEEN SENT TO LHM | 2024-07-21 |  |  |  |  | CORROSION CONTROL PROGRAMME (CCP)
[5 empty] | ON 23 FEB 2023 | [5 empty] | 7 Days CCP |  | 2022-10-13 |  | -377
[11 empty] | 1 Mth CCP |  | 2022-11-07 |  | -352 | FLOATATION SYS
[11 empty] | 3 Mth CCP |  | 2022-10-28 |  | -362 | INSTALLED
[5 empty] | FRAME STA 5700 REPLACEMENT | [5 empty] | 6 Mth CCP |  | 2022-10-28 |  | -362
ENG #2 |  |  |  |  | IN PROGRESS
NIL | ENG #2
| NIL | [9 empty] | SERVICE BULLETIN / AIRWORTHINESS DIRECTIVE
[11 empty] | ASB139-654 (Part II) - Main Rotor Swashplate Boot Insp - EVERY 50FH | 2824 |  | 20.2 |  | LIFE RAFT
[11 empty] | BT139-443 (Every 6 Month Hoist Load Test) |  | 2022-12-20 |  | -309 | REMOVED
[11 empty] | ASB139-724 REV B - TR Damper Bracket Insp. (50FH/2M) | 2842.1 | 2022-11-19 | 38.3 | -340 | SER NO:
AC LANDING CYCLE
[11 empty] | SB139-728 TR Duplex Bearing Insp (Part I) | 2853.8 | 2022-12-11 | 50 | -318 | 4346
[11 empty] | COMPONENT | SERVICING / ANNUAL |  | O/HAUL
[11 empty] | Emergency Floats (Annual Insp) | 2022-11-30
[11 empty] | ELT battery Pack SN: 375581-036 | 2022-11-30 | -329 |  |  | FUEL
[11 empty] | Clutch Assy PN: 44314-398-101 SN: l72-94 (Due 40 Mth) - RESCUE HOIST |  |  | 2022-11-29 | -330
.
.
30